## Sheet 1 - Blockchain Team Lithi
Blockchain Team Lithium - Project Plan
Task Name | Due Date | Status | Start Date
Sprint 1 | December 22nd 2020
Project initilization and planning | December 1st 2020 | in progress | November 29th 2020
Requirement gathering | December 6th 2020 | in progress | December 1st 2020
Hyperledger fabric test network analysis | December 10th 2020 | Open | December 1st 2020
Analyse Hyperledger Components | December 5th 2020 | Open | December 1st 2020
Relating Scenario to Hyperledger Fabric Components | December 10th 2020 | Open | December 6th 2020
Design | December 20th 2020 | Open | December 12th 2020
System design | December 15th 2020 | Open | December 12th 2020
Model design | December 20th 2020 | Open | December 16th 2020
Implementation | December 22nd 2020 | Open | December 18th 2020
Network creation | December 22nd 2020 | Open | December 18th 2020
Sprint 2 | January 12th 2021
Network administration |  | Open
Implementation - backend |  | Open
Smart contracts |  | Open
UI design for all screens |  | Open
Implementation - frontend |  | Open
Screen for doctor |  | Open
Screen for patient |  | Open
Integration |  | Open
Sprint 3 | February 9th 2021
Implementation backend |  | Open
Implementation frontend |  | Open
Testing |  | Open
Unit testing |  | Open
Integration |  | Open
Sprint 4 | March 31st 2021
Implementation - pending tasks |  | Open
Prepare report |  | Open
Prepare presentation |  | Open
Testing |  | Open
Acceptance |  | Open
System |  | Open